# Project Horizon — Weekly Status Update

Week ending: 24 February 2026

Prepared by: Priya Ramesh

## Progress

We are tracking against the revised four-deliverable scope confirmed at the steering committee on 10 February. Databricks on DataCorp Cloud is provisioned; Power BI workspace is partially built; the newly-added data-quality monitoring component is in design.

## Deliverables Status

(a) Databricks workspace — 80% complete, DataCorp Cloud provisioned.

(b) Power BI reports — 50% complete.

(c) Knowledge transfer — not started (planned for final fortnight).

(d) Data-quality monitoring — 20% complete (added post-10-Feb steering).

## People

Marcus Lee has given notice and will roll off the project on 7 March. Handover plan needed. Priya to request formal handover document from Marcus by 3 March.

## Deadline

Targeting 30 March final delivery per revised steering committee scope.

## Risks & Escalations

Vendor lock-in concern with DataCorp Cloud flagged in the risk register. Jun Park (NorthWind CTO) has asked for confirmation that the vendor switch aligns with their procurement standards.